## RIDP DETAILS
RIDP
Rural Infrastructure Development Programme - 2020
Physical and Financial Progress of the Month of 18/12/ 2020
Division : moratuwa
1. Serial No |  | 2. Project No | 3 Name of the Project | GN Division |  | 6 Name of Minister / Member of Parliament/ Officer who proposed the project | Key Performance Indicators |  | 9 Approved Amount (Rs.) | 10 Implementing Agency |  | Progress |  |  | 15 No of Beneficiaries | 16 Starting Date | 17 End Date
| Division | [10 empty] | Financial
14 Total Expenditure (Rs.)
|  |  |  | 4 GN Division No | 5 GN Division Name |  | 7 Length/Area (m./k.m./sq.m.) | 8 Value of Measurement |  |  | 11 Estimate Total (Rs) | 12 Expenditure (Work Done) | 13 Admin expenditure (0.5%)
1 | Moratuwa | 2020/RDP/MTS/MOR/002 | Development of the sanitation system of Prince of Wales College, Moratuwa | 557ඒ | Rawathawaththa west | Ministry of Finance ,Economy and policy Development | sqr | 16 | 500000 | SDS | 496542.31 | 370000 | 1850 | 371850 | 2000 | 2020-11-20 | 2020-12-20
2 | Moratuwa | 2020/RDP/MTS/MOR/06 | Development of 1st Cross Road of Railway Station Road | 547A | Agulana South | Ministry of Finance ,Economy and policy Development | m | 40.48 | 500000 | MMC | 488972.7 | 486540 | 2432.7 | 488972.7 | 20 | 2020-11-20 | 2020-12-21
3 | Moratuwa | 2020/RDP/MUG/MOR/010 | Reconstruction of Yogarashrama Mawatha drainage system at Thelawala | 549A | Thelawala North | Ministry of Finance ,Economy and policy Development | m | 28.42 | 700000 | MMC | 692686.67 | 689240.47 | 3446.2 | 692686.67 | 160 | 2020-11-22 | 2020-12-22
4 | Moratuwa | 2020/RDP/MUG/MOR/011 | Development of the inner road from the old road of the third lane of Koralawella and preparing a shoe drain | 554 | Koralawella North | Ministry of Finance ,Economy and policy Development | m | 10.75 | 700000 | MMC | 660085.77 | 656801.77 | 3284 | 660085.77 | 284 | 2020-11-23 | 2020-12-23
5 | Moratuwa | 2020/RDP/MUG/MOR/012 | Construction of drainage system from Koralawella Asiri Mawatha to the new Galle Road | 555 | Koralawella North | Ministry of Finance ,Economy and policy Development | m | 139.8 | 600000 | MMC | 595950.12 | 592985.2 | 2964.92 | 595950.12 | 385 | 2020-11-24 | 2020-12-24
6 | Moratuwa | 2020/RDP/MTS/MOR/016 | Development of Madangahawatta Community Hall access road | 553 | Moratuwella South | Ministry of Finance ,Economy and policy Development | m | 106.1 | 500000 | MMC | 450215.3 | 418027.2 | 2090.14 | 420117.34 | 27 | 2020-11-25 | 2020-12-25
7 | Moratuwa | 2020/RDP/MTS/MOR/017 | Carpeting in front of the temple at the corner of the Peace Vihara on Borupana Peace Temple Road | 549A | Borupana | Ministry of Finance ,Economy and policy Development | m | 208 | 1000000 | MMC | 864839.8 | 860537.12 | 4302.68 | 864839.8 | 180 | 2020-11-26 | 2020-12-26
[8 empty] | 549.55 | 4500000 |  | 4249292.67 | 4074131.76 | 20370.64 | 4094502.4 | 3056

## RIDP SUMMARY
RIDP
Rural Infrastructure Development Programme- 2020 | [24 empty] | Annexure E
Physical and Financial Progress as at 18/12/2020
District :Colombo Divition - Moratuwa
No | Division | No of Projects Approved | Total categorized by Sectors * | [7 empty] | Approved Amount (Rs) | Approved Amount (Rs. Mn.) | Expenditure (Rs) | Progress | [10 empty] | No. of Beneficiaries | Remark (Bills In Hand)(Rs)
|  |  | RA | EI | LD | EL | WS | SD | AI | OI |  |  |  | Financial | Physical ***
[14 empty] | Expenditure (Rs. Mn.) | A | B |  |  |  | C | D | E | F | G
[16 empty] | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4)
| moratuwa | 13 | Total categorized by Sectors * RA: 11; Total categorized by Sectors * OI: 2 | 8000000 | 8 | 4094502.4 | 4.09 | 3 | 3 | [7 empty] | 7 | 3056 | 3 Amended Projects
Total |  | 13 | Total categorized by Sectors * RA: 11; Total categorized by Sectors * OI: 2 | 8000000 | 8 | 4094502.4 | 4.09 | 3 | 3 | [7 empty] | 7 | 3056 | 3 Amended Projects
* Projects should be categorized for following sectors | [11 empty] | *** Physical progress
RA - Rural Access ( Roads, Bridges, Culverts…..) | [11 empty] | A - Estimates are being / to be prepared
EI - Economic Infrastructure | [11 empty] | B - For Constructions : B-1- Estimates Approved & Bid Documents Prepared, B-2- Quotation / Bid called, B-3- Quotation / Bid Received , B-4- Contract Awarded
LD - Livelihood Development | [11 empty] | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimate prepared
EL - Rural Electricity | [11 empty] | C - For Constructions : Start construction work ,40% completed, Other : placed order for goods
WS - Water Supply ( Drinking Water) | [11 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
SD - Sports Development (Play grounds, Jogging tracks……….) | [11 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order
AI - Agriculture & Irrigation | [11 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
OI - Other Infrastructure ( including Health and Education) | [11 empty] | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs